## Project Schedule
Project Schedule
Task Name | Responsible | Start | End | Days | Status
Requirement Gathering and Analysis | All | 2016-08-04 | 2016-09-10 | 37 | Complete
Analysis of existing systems | All | 2016-08-04 | 2016-08-11 | 7 | Complete
Feasibility Study | All | 2013-08-13 | 2016-08-25 | 12 | Complete
Interviews | Mansi, Jaspreet, Hardik Bohra, Chintan | 2016-08-25 | 2016-09-01 | 7 | Complete
BrainStorming | All | 2016-08-12 | 2016-09-01 | 20 | Complete
Creating product backlog | All | 2016-08-19 | 2016-09-11 | 23 | Complete
Sprint 1(User Management) |  | 2016-09-12 | 2016-10-02 | 20 | In progress
1. Fixing Functional requirements and Creating Sprint Backlog | All | 2016-09-12 | 2016-09-15 | 3 | Complete
2. Learning Node Js and Mongo Db | Jaspreet, Bohra, thakkar | 2016-09-15 | 2016-09-30 | 15 | Complete
3. Learning React JS and Create JS | All | 2016-09-15 | 2016-09-30 | 15 | Complete
4. Building Database Schema | All | 2016-09-12 | 2016-09-15 | 3 | Complete
5. Building Rest API | All | 2016-09-15 | 2016-09-18 | 3 | Complete
Web Interface
W1. User Management | Palash, Fatema, Mansi, Chintan | 2016-09-25 | 2016-10-02 | 7 | Working
W1.1 User Authentication/registeration | Mansi, Chintan | 2016-09-25 | 2016-09-29 | 4 | Working
W1.2 Login | Fatema | 2016-09-30 | 2016-10-02 | 1 | Working
W2. Web interface Design(Wireframe) | Palash | 2016-09-15 | 2016-09-30 | 15 | Working
Mobile Application
M1. User Management | Dishant, Jaspreet, Bohra, Thakkar | 2016-09-25 | 2016-10-02 | 7 | Working
A1.1 User Authentication/registeration | Bohra, Jaspreet | 2016-09-25 | 2016-09-29 | 4 | Working
A1.2 Login | Thakkar, Dishant | 2016-09-30 | 2016-10-02 | 1 | Working
M2. Game Graphics | Kush | 2016-09-15 | 2016-09-30 | 15 | Working
Sprint 2(User Management and Mobile Game) |  | 2016-10-02 | 2016-10-22 | 20 | In progress
1. Creating Sprint Backlog | All | 2016-10-03 | 2016-10-04 | 1 | Not started
2. Updating Rest API | Bohra, Jaspreet | 2016-10-03 | 2016-10-04 | 1 | Not started
Web Interface
W1. User Management | Fatema, Mansi | 2016-10-04 | 2016-10-06 | 2 | Not started
W1.1 Profile Management | Fatema, Mansi | 2016-10-04 | 2016-10-06 | 2 | Not started
W2. Course Management | Mansi, Chintan, Fatema | 2016-10-04 | 2016-10-12 | 8 | Not started
W2.1 Add Course | Chintan | 2016-10-04 | 2016-10-12 | 8 | Not started
W2.2 Update Course | Mansi | 2016-10-04 | 2016-10-12 | 8 | Not started
W2.3 Deactivate Course | Fatema | 2016-10-04 | 2016-10-12 | 8 | Not started
W2. Game Management | Mansi, Chintan, Fatema | 2016-10-13 | 2016-10-21 | 8 | Not started
W2.1 Add Unit/Topic | Mansi, Chintan, Fatema | 2016-10-13 | 2016-10-21 | 8 | Not started
W3. Implementing design according to wireframes | Palash | 2016-10-04 | 2016-10-21 | 17 | Not started
Mobile Application
M1. Game Development and Course Selection | Dishant, Jaspreet, Bohra, Thakkar | 2016-10-04 | 2016-10-21 | 17 | Not started
M1.1 Unit 1 Game - Level 1 | Dishant,Thakkar | 2016-10-04 | 2016-10-12 | 8 | Not started
M1.2 Unit 2 Game - Level 1 and View Courses | Bohra, Jaspreet | 2016-10-04 | 2016-10-12 | 8 | Not started
M1.3 Unit 1 Game - Level 2 and Register Course | Dishant,Thakkar | 2016-10-12 | 2016-10-21 | 9 | Not started
M1.4 Unit 2 Game - Level 2 and Unregister Course | Bohra, Jaspreet | 2016-10-12 | 2016-10-21 | 9 | Not started
M1.5 Register and Deregister for a Course | Bohra, Jaspreet, Thakkar | 2016-10-17 | 2016-10-21 | 4 | Not started
M2. Game Graphics | Kush | 2016-10-04 | 2016-10-21 | 17 | Not started
3. Testing and Sprint Review | All | 2016-10-21 | 2016-10-22 | 1 | Not started
Sprint 3(Mobile Game and Game Management) |  | 2016-10-23 | 2016-11-12 | 20 | Not started
1. Creating Sprint Backlog | All | 2016-10-23 | 2016-10-24 | 1 | Not started
2. Updating Rest API | Bohra, Jaspreet | 2016-10-23 | 2016-10-24 | 1 | Not started
Web Interface
W1. Game Management | Fatema, Mansi | 2016-10-24 | 2016-11-03 | 10 | Not started
W1.1 Manage Unit/Topic | Fatema, Mansi | 2016-10-24 | 2016-11-03 | 10 | Not started
W1.1 Manage Points | Chintan | 2016-10-24 | 2016-11-03 | 10 | Not started
W2. Manage Materials | Mansi, Chintan, Fatema | 2016-11-03 | 2016-11-08 | 5 | Not started
W2.1 Add Material | Chintan | 2016-11-03 | 2016-11-08 | 5 | Not started
W2.2 Update Material | Mansi, fatema | 2016-11-03 | 2016-11-08 | 5 | Not started
W3. Implementing design according to wireframes | Palash | 2016-10-23 | 2016-11-08 | 16 | Not started
Mobile Application
M1. Game Development | Dishant, Jaspreet, Bohra, Thakkar | 2016-10-24 | 2016-11-03 | 10 | Not started
M1.1 Unit 3 Game - Level 1 | Dishant,Thakkar | 2016-10-24 | 2016-11-03 | 10 | Not started
M1.2 Unit 3 Game - Level 2 | Bohra, Jaspreet | 2016-10-24 | 2016-11-03 | 10 | Not started
M2. Mobile Game | Dishant, Jaspreet, Bohra, Thakkar | 2016-11-03 | 2016-11-08 | 5 | Not started
M2.1 View and Serach Unit | Dishant,Thakkar | 2016-11-03 | 2016-11-08 | 5 | Not started
M2.2 Attempt Unit | Bohra, Jaspreet | 2016-11-03 | 2016-11-08 | 5 | Not started
A2. Game Graphics | Kush | 2016-10-24 | 2016-11-08 | 15 | Not started
3. Unit Testing | All | 2016-11-08 | 2016-11-09 | 1 | Not started
4. Integration Testing | All | 2016-11-09 | 2016-11-10 | 1 | Not started
5. Bug Fixation | All | 2016-11-10 | 2016-11-11 | 1 | Not started
6. Sprint Review | All | 2016-11-11 | 2016-11-12 | 1 | Not started
Sprint 4(Announcements and Performance Statistics) |  | 2016-11-13 | 2016-11-30 | 17 | Not started
1. Creating Sprint Backlog | All | 2016-11-13 | 2016-11-14 | 1 | Not started
2. Updating Rest API | Bohra, Jaspreet | 2016-11-13 | 2016-11-14 | 1 | Not started
Web Interface
W1. Manage Announcements | Fatema, Mansi | 2016-11-14 | 2016-11-19 | 5 | Not started
W3. Implementing design according to wireframes | Palash | 2016-11-14 | 2016-11-19 | 5 | Not started
Mobile Application
M1. Overall Performance | Dishant, Jaspreet, Bohra, Thakkar | 2016-11-14 | 2016-11-18 | 4 | Not started
M1.1 View Leaderboard | Dishant,Thakkar | 2016-11-14 | 2016-11-18 | 4 | Not started
M1.2 View Statistics | Bohra, Jaspreet | 2016-11-14 | 2016-11-18 | 4 | Not started
M2. View Tutorial and Anouncements | Dishant, Jaspreet, Bohra, Thakkar | 2016-11-18 | 2016-11-22 | 4 | Not started
M2.1 View Tutorials | Dishant,Thakkar | 2016-11-18 | 2016-11-22 | 4 | Not started
M2.2 View Announcements | Bohra, Jaspreet | 2016-11-18 | 2016-11-22 | 4 | Not started
A2. Game Graphics | Kush | 2016-11-14 | 2016-11-22 | 8 | Not started
3. Unit Testing | All | 2016-11-22 | 2016-11-24 | 2 | Not started
4. Integration Testing | All | 2016-11-24 | 2016-11-26 | 2 | Not started
5. Integration Testing | All | 2016-11-26 | 2016-11-28 | 2 | Not started
6. Bug Fixation | All | 2016-11-28 | 2016-11-29 | 1 | Not started
7. Deployment | All | 2016-11-29 | 2016-11-30 | 1 | Not started

## Gantt Chart
Task Name | Start | End | Days
Requirement Gathering and Analysis | 2016-08-04 | 2016-08-19 | 15
Creating product backlog | 2016-08-19 | 2016-09-11 | 23
Building Database Schema | 2016-09-12 | 2016-09-15 | 3
Building Rest API | 2016-09-15 | 2016-09-18 | 3
W1. User Management | 2016-09-25 | 2016-10-06 | 11
M1. User Management | 2016-09-25 | 2016-10-02 | 7
W2. Course Management | 2016-10-04 | 2016-10-12 | 8
M2. Game Development | 2016-10-04 | 2016-11-03 | 30
W3. Game Management | 2016-10-24 | 2016-11-03 | 10
W4. Manage Materials | 2016-11-03 | 2016-11-08 | 5
M3. Mobile Game | 2016-11-03 | 2016-11-08 | 5
W5. Manage Announcements | 2016-11-14 | 2016-11-19 | 5
M4. Overall Performance | 2016-11-14 | 2016-11-18 | 4
M5. View Tutorial and Anouncements | 2016-11-18 | 2016-11-22 | 4
Unit Testing | 2016-11-22 | 2016-11-24 | 2
Integration Testing | 2016-11-24 | 2016-11-26 | 2
Integration Testing | 2016-11-26 | 2016-11-28 | 2
Bug Fixation | 2016-11-28 | 2016-11-29 | 1
Deployment | 2016-11-29 | 2016-11-30 | 1
Milestone
06-Oct-2016
02-Oct-2016
12-Oct-2016
08-Nov-2016
19-Nov-2016
18-Nov-2016
24-Nov-2016
08-Nov-2016
03-Nov-2016
03-Nov-2016